## DESC Projects
Project ID | Project Name / Endpoints (raw title) | Description | Need / Area Note | Status | Planned In-Service Date
6807 B | Queensboro - Ft Johnson 115 kV & Queensboro-Bayfront 115kV (Queensboro-James Island Sect) | Replace the Queensboro – Ft Johnson 115 kV Line and structures as they have reached the end of life. | This project is required due to address end of life issues. | In Progress | 12/31/23
0167C-D | Union Pier 115-13.8 kV Sub: Tap | Installing a 115 kV Tap to feed the future Union Pier 115 kV Sub. | This project is needed to for load growth in the Charleston area. | Planned | 12/31/27
0139 M,N | Okatie 230-115kV Substation, Jasper – Yemassee 230kV #1 Fold-in | Expand existing Okatie Transmission sub, add a 230-115 autobank and fold the Jasper – Yemassee 230 kV #1 line into the 230 kV side. Construct two additional 115 kV bus tie lines. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | In Progress | 12/31/2024
6341 A-F | Cainhoy - Hamlin 115kV: Rebuild Line and Cainhoy – Hamlin 115 kV #2: Construct New 115 kV Line | Upgrade the 954 ACSR portion of the Cainhoy – Hamlin 115 kV line to B795 ACSR conductor, construct a new Cainhoy – Hamlin 115 kV #2 line, add terminals to Cainhoy and Hamlin sub to accommodate upgrades. | This project is required due to load growth in the Mount Pleasant area and to meet NERC TPL and internal DESC Planning criteria. | In Progress | 12/01/25
6808 J | Eastover - Square D 115kV: Rebuild | Replace wooden H-Frame structures with Self Supporting Steel Structures and restring with 1272 ACSR conductor. | This project is required to address end of life and reliability issues on these lines. | In Progress | 06/01/24
6808 K | Burton-St Helena 115kV: Rebuild Burton-Frogmore Transmission Section | Replace wooden structures with Self Supporting Steel Structures and restring with 1272 ACSR conductor for the Burton – Frogmore Transmission section. | This project is required to address end of life and reliability issues on these lines. | In Progress | 12/31/24
6808 L | Burton-St Helena 115kV: Frogmore Distribution - St Helena | Replace wooden structures with Self Supporting Steel Structures and upgrade to 795 ACSR for the Frogmore Distribution Tap – St. Helena section. | This project is required to address end of life and reliability issues on these lines. | In Progress | 12/31/25
6808 N,O | VCS1-Denny Terrace 230kV & VCS1-Pineland 230kV: Rebuild Single Circuit Sections | Replace wooden H-Frame structures with Self Supporting Steel Structures and restring with standard 1272 ACSR conductor. | This project is required to address end of life and reliability issues on these lines. | In Progress | 12/31/26
6808 R | Wateree-Killian 230kV: Rebuild | Replace wooden H-Frame structures with Self Supporting Steel Structures. | This project is required to address end of life and reliability issues on these lines. | In Progress | 12/31/28
6808 S | Okatie-Bluffton 115kV: Rebuild | Replace wooden H-Frame structures with Self Supporting Steel Structures and upgrade conductor to standard 1272 ACSR. | This project is required to address end of life and reliability issues on these lines. | In Progress | 06/01/2025
6808 U | Hopkins-CIP 230kV: Rebuild | Replace wooden H-Frame structures with Self Supporting Steel Structures. | This project is required to address end of life and reliability issues on these lines. | Planned | 12/31/25
6808 V | Faber Place-Bayfront 115kV: Rebuild North Bridge Terrace to Bayfront Section | Replace wooden structures with Self Supporting Steel Structures and upgrade conductor to standard 1272 ACSR. | This project is required to address end of life and reliability issues on these lines. | Planned | 12/31/28
6808 W | Square D - Hopkins 115kV: Rebuild | Replace wooden H-Frame structures with Self Supporting Steel Structures and restring with 1272 ACSR conductor. | This project is required to address end of life and reliability issues on these lines. | In Progress | 9/30/2024
6809 E | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV Rebuilds | 9.5 miles. Scope includes rebuilding the 115 and 46 kV lines in this corridor SPDC. | This project is required to address end of life and reliability issues on these lines. | In Progress | 12/31/24
6809 G | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV | Upgrade 6.5 miles of aging conductor with 1272 ACSR and rebuild with SPDC. | This project is required to address end of life and reliability issues on these lines. | Planned | 12/31/25
6805 G | Edenwood Sub: #1 & #2 230-115kV Autobanks, Replace with 336MVA | Replace Autobank 1 and 2 at Edenwood Substation. | This project is required to address end of life and maintenance issues on these transformers. | In Progress | 12/25/24
1060A, I, L | Williams St Sub: Replace Sw House & Relays, AM Williams Sub: Replace Sw House, and McMeekin Sub: Add Sw House | Replace switch house, switch house equipment, and relay panels at Williams Street substation. Replace the switch house at AM Williams substation. Add Switching House at McMeekin Substation to move relays from plant relay room. | This project is required to address end of life and maintenance issues on these transformers. | In Progress | 12/31/28
06005 B | Harleyville 115KV Transmission Tap – Construct (1.4 miles) | Extend the 115 kV line from the Blue Circle tap to the Harleyville substation to provide 115 kV service. | Load growth. | Planned | 3/31/2027
05004 P | Summerville: Replace and Spare 230-115kV 336MVA Auto Bank | Purchase a spare 230/115kV, 336MVA Autobank for the Southern Region to be stored at Summerville 230kV Sub. Include a pad, AC for heaters, and possibly a pit for oil containment. | Spare equipment needs. | In Progress | 12/31/2024
06076A | Canadys-Ritter 115KV-Rebld SPDC 230/115KV 1272 (Approx 18 Miles) | Rebuild Canadys-Ritter 115 kV line as SPDC with 230 kV on one side and 115 kV on the other side. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | In Progress | 6/1/2026
6359 | Yemassee– Ritter 230kV #1 & #2: Construct SPDC with B-1272 | Construct Ritter – Yemassee 230kV #1 and #2 SPDC with B1272 ACSR on both sides. Convert the existing Ritter – Yemassee 230 kV to 115 kV operation. Convert and add terminals at Ritter and Yemassee. Add 230 kV bus tie at Ritter and upgrade the Yemassee 230 kV bus tie. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | Planned | 6/1/2026
06367 A - C, H | Riverport Tap: Construct Tap | Construct Okatie – Riverport 230 kV to feed new Distribution substation. | Load growth. | In Progress | 12/31/25
06367 D - G | Jasper – Okatie 230 kV #2: Construct | Construct a 230 kV line with B1272 ACSR from Jasper to Okatie 230/115kV Substation. The line is estimated to be 6.5 miles long. This makes Jasper a Medium Impact substation and will require a new CIP Hut. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | In Progress | 12/31/25
06371 D | Wagener 115kV Tap: Construct Tap | Constructing a 115 kV Tap off the Edmund Switching Station- Owens Corning 115 kV Line to feed new Wagener Distribution substation. | Load growth. | Planned | 12/31/25
06372 A | Church Creek - Ritter 230kV - Replace 38 Large Angles and Dead Ends | Replace 6.5 miles of aging conductor. | Replacing approximately 38 guyed wooden structures due to recent failures in the fiberglass strain insulators along this line. Structures to be changed out are dead ends/large angles. | In Progress | 6/1/2024
06810 F | VCS2-Ward 230kV: Rebuild Line | Rebuild 40 miles of 230 kV line. | This project is required to address end of life and maintenance issues. | Planned | 12/31/29
06810 G | Goose Creek Reservoir: Rebuild Transmission Line Crossings | Rebuilding the Williams Goose Creek 230 and 115 kV lines and the Williams - Faber Place 230 kV line across the Goose Creek Reservoir. | This project is required to address end of life and maintenance issues. | In Progress | 12/31/24
06810 H | Summerville 115kV Loop: Rebuild | Replacing several wood pole sections on the Summerville 115 kV Loop that have reached the end of life. | This project is required to address end of life and maintenance issues. | In Progress | 12/31/24
6809 M | St George - Sumter 230kV Tie: Rebuild Line from Santee Substation - Duke/Progress Energy Tie | Rebuild Line from Santee Substation - Duke/Progress Energy Tie. | Grid hardening. | Planned | 12/31/2025
5392 A-C | Coit – Gills Creek 115kV: Construct | Convert the existing Coit - Gills Creek 33 kV Line to 115 kV. Approximately 1.25 miles. Construct Gills Creek Terminal at Coit Bus #1. | Load growth. | In Progress | 12/31/2024
6810 A | Hooks - Thurmond 115kV Tie: Rebuild | Rebuilding section of line between Hooks and Thurmond. Approximately 2.3 miles. The line will be rebuilt on existing R/W using steel poles, 115 kV insulation, and 1272 ACSR conductor. | This project is required to address end of life and reliability issues on these lines. | In Progress | 12/31/2024
6809 N | Batesburg - Saluda County 115kV: Rebuild | Rebuild 13.5 miles of conductor. | Grid hardening. | In Progress | 12/31/2025
6853 B-F | Scout 230 kV Sub and Fold-in: Construct | Construct 230kV Transmission Line for Scout Customer Substation and modify VCS1 and Killian terminals. | Load growth. | In Progress | 3/31/2026
6859 | Dawson 230kV Sub and Fold-in: Construct and Rebuild | Construct Dawson 230kV substation. Fold in the existing Canadys – Church Creek and Canadys – Faber Place 230kV lines at the Dawson 230kV substation (phase 1). Rebuild Canadys – Dawson 230kV #1 and #2 with B1272 ACSR (phase 2). | Load growth. | In Progress | 10/1/2025 (phase 1) and 10/1/2026 (phase 2)
6852 | Urquhart – Toolebeck 115kV line: Rebuild | Upgrade the 477 ACSR portions of the Urquhart – Toolebeck 115 kV line to 1272 ACSR. Replace existing structures with Single Pole Double Circuit Structures. Approximately 12.5 miles. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | In Progress | 8/12/2026
6388 A | Williams-Summerville 230kV: Upgrade to SPDC B1272 ACSR | Rebuild the section of the Williams - Summerville 230 kV line from Ladson Jct to Williams. Line to upgraded to B-1272 and designed for a future second circuit. Approximately 10 miles. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | Planned | 5/1/2027
0147 C, K | Cainhoy 115 kV Tap: Construct | Construct a 115 kV tap from Cainhoy to Clements Ferry. Approximately 2.8 miles. Construct terminal at Cainhoy. | Load growth. | Planned | 12/31/2027
0147 B, J | Jack Primus 115 kV Tap: Construct | Construct a 115 kV tap from Jack Primus to Clements Ferry. Approximately 2.2 miles. Construct terminals at Jack Primus. | Load growth. | Planned | 12/31/2027
6847 A-B, D-H | Church Creek – Faber Place – Charleston Transmission: Add 230kV Line | Construct a 230 kV transmission line from Church Creek to Charleston Transmission. The Church Creek – Faber Place 230kV and 115kV lines will be rebuilt, and a 230kV line will be added between Faber Place and Charleston Transmission. Add 230/115kV transformer at Charleston Transmission. Add/upgrade terminals and bus work at impacted substations. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | In Progress | 05/01/2027
6846 A | Eastover – Sumter 115kV DEP Tie: Rebuild with 1272 ACSR | Upgrade the DESC section (approx. 1 mile) of the tie line from 397.5 ACSR Ibis to 1272 ACSR. | This project is needed to improve system performance and to meet NERC TPL and internal DESC Planning Criteria for reliability. | Planned | 05/31/2026
6810 U | Cameron Jct – Elloree 46 kV Rebuild | Rebuilding the Cameron Jct – Elloree 46 kV Line. 7.3 miles. | System hardening | Planned | 12/31/2026
6810 J | Elloree – Santee City 46 kV: Rebuild | Rebuilding the 46 kV line between Elloree and Santee City. 7 miles. | System hardening | Planned | 12/31/2027
6810 O | Urquhart – Aiken PSA 46 kV: Rebuild | Rebuilding the section of 46 kV line from Urquhart to the Aiken PSA tap point. TBD if the scope of this project includes rebuilding the actual tap Aiken PSA. 4.5 miles. | System hardening | Planned | 12/31/2027
6810 T | Cameron Jct – Cameron – St Matthews 46 kV Rebuild | Rebuilding the 46 kV line between Cameron Jct and St Matthews. 9.8 miles. | System hardening. | Planned | 12/31/2028

## GA ITS Projects
Zone | TEAMS Number | Project Name / Endpoints (raw title) | Sponsor (GPC/GTC/MEAG/DU/SAV) | Year Filed | Need / In-Service Date
216 | 19631 | PINE GROVE PRIMARY 115 KV DUAL STAGE CAPACITOR BANK | GPC | 2025 | 6/1/2025
219 | 20067 | SAV: DEPTFORD - MAGNOLIA 115KV RECONDUCTOR | SAV | 2025 | 6/1/2025
214 | 20466 | SMART VALVE INSTALLATION | GPC | 2025 | 6/1/2025
218 | 21046 | THALMANN AND COLERAIN 23O KV LINE RELAY PANEL UPGRADES | GPC | 2025 | 6/1/2025
211 | 20431 | VILLA RICA LOW SIDE BREAKER | GPC | 2025 | 6/1/2025
218 | 20684 | CAMDEN INDUSTRIAL PARK (GPC) | GPC | 2025 | 6/1/2025
213 | 18774 | GTC: HEARD COUNTY - TENASKA 500KV (SECOND LINE) | GTC | 2025 | 12/1/2025
206 | 18889 | JEFFERSON STREET#3 - NORTHWEST (WHITE) 115 KV RECONDUCTOR | GPC | 2025 | 12/1/2025
212 | 20326 | ANTHONY SHOALS STATCOM SYSTEM | GPC | 2025 | 12/31/2025
211 | 20152 | CC - CASS PINE- HILL VIEW 230 KV LINE- CC IMPROVEMENTS | GPC | 2025 | 12/31/2025
211 | 20175 | CC - PROJECT CHRONOS- SK/HYUNDAI | GPC | 2025 | 12/31/2025
215 | 20010 | GTC: ANTHONY SHOALS - WASHINGTON 115 KV LINE REBUILD | GTC | 2025 | 12/31/2025
219 | 17075 | SAV: LITTLE OGEECHEE 230- 115KV: RELAY MODERNIZATION | SAV | 2025 | 12/31/2025
216 | 18691 | GTC: LIZARD LOPE - WESTOVER 115 KV NEW LINE | GTC | 2026 | 3/1/2026
208 | 20018 | CC - QTS FAYETTEVILLE TRANSMISSION NEEDS | GPC | 2026 | 4/1/2026
208 | 19597 | ADAMSVILLE - BUZZARD ROOST 230KV REBUILD AND JUMPER UPGRADE | GPC | 2026 | 6/1/2026
201 | 18960 | BLANKETS CREEK – WOODSTOCK 115KV LINE REBUILD | GPC | 2026 | 6/1/2026
201 | 20243 | CC - GARRETT ROAD SWITCHING STATION - TRAE LANE | GPC | 2026 | 6/1/2026
208 | 20216 | CC - STONEWALL TELL ROAD (TA REALTY) | GPC | 2026 | 6/1/2026
211 | 18679 | DU: EAST DALTON - OOSTANAULA 115KV REBUILD | DU | 2026 | 6/1/2026
208 | 20491 | EAST POINT RELAY MODERNIZATION | GPC | 2026 | 6/1/2026
215 | 16007 | FENWICK STREET - SAND BAR FERRY 115KV (RECONDUCTOR/REBUILD) | GPC | 2026 | 6/1/2026
213 | 20516 | GOAT ROCK 230KV SWITCH, JUMPER, & LINE TRAP REPLACEMENT | GPC | 2026 | 6/1/2026
214 | 19618 | GORDON-N DUBLIN 115KV (GORDON-ENGL MCI J) REBUILD | GPC | 2026 | 6/1/2026
206 | 21139 | GRADY - MORROW (WHITE) 115KV REBUILD | GPC | 2026 | 6/1/2026
206 | 20474 | GRADY 230/115KV RELAY MODERNIZATION | GPC | 2026 | 6/1/2026
212 | 19706 | GRID - GAINESVILLE #2 EQUIPMENT REPLACEMENT | GPC | 2026 | 6/1/2026
206 | 21137 | GTC: CONYERS - CORNISH MOUNTAIN 115KV LINE UPGRADE | GTC | 2026 | 6/1/2026
213 | 19334 | GTC: LAGRANGE - NORTH OPELIKA 230 KV | GTC | 2026 | 6/1/2026
212 | 20015 | GTC: MORNING HORNET 2ND 230/115 KV BANK & THUMBS UP 115KV TL | GTC | 2026 | 6/1/2026
214 | 19999 | GTC: ROBINS SPRING BUS REPLACEMENT | GTC | 2026 | 6/1/2026
214 | 20001 | GTC: ROBINS SPRING CAPACITOR BANK INSTALLATION | GTC | 2026 | 6/1/2026
211 | 19636 | HAMMOND - WEISS DAM 115KV LINE REBUILD | GPC | 2026 | 6/1/2026
214 | 20512 | KATHLEEN AREA IMPROVEMENTS | GPC | 2026 | 6/1/2026
206 | 20490 | KLONDIKE RELAY MODERNIZATION | GPC | 2026 | 6/1/2026
213 | 19598 | MEAG: DRESDEN - LAGRANGE PRIMARY 230KV UPGRADE & JUMPERS | MEAG | 2026 | 6/1/2026
215 | 20270 | MEAG: RAY PLACE RD - WASHINGTON #3 | MEAG | 2026 | 6/1/2026
215 | 20271 | MEAG: RAY PLACE RD - WASHINGTON (WASHINGTON - WASHINGTON 3) | MEAG | 2026 | 6/1/2026
208 | 20300 | MORROW 115KV RELAY UPGRADE | GPC | 2026 | 6/1/2026
216 | 18690 | PALMYRA REACTOR REMOVAL | GPC | 2026 | 6/1/2026
219 | 20066 | SAV: BOULEVARD - DEPTFORD 115KV RECONDUCTOR | SAV | 2026 | 6/1/2026
219 | 19966 | SAV: CC - BIG OGEECHEE 500/230KV (CC NETWORK IMPROVEMENTS) | SAV | 2026 | 6/1/2026
219 | 20277 | SAV: MCINTOSH - PURRYSBURG 230KV REACTORS | SAV | 2026 | 6/1/2026
206 | 20489 | SCOTTDALE RELAY MODERNIZATION | GPC | 2026 | 6/1/2026
208 | 17900 | UNION CITY - YATES 230 KV WHITE LINE REBUILD | GPC | 2026 | 4/1/2026
208 | 20691 | UNION CITY - YATES 230KV (WHITE) SWITCH AND TRAP REPLACEMENT | GPC | 2026 | 6/1/2026
216 | 20223 | CC - PROJECT PAYTON BAINBRIDGE | GPC | 2026 | 6/30/2026
208 | 21022 | OHARA BREAKER REPLACEMENT | GPC | 2026 | 10/1/2026
208 | 20668 | DRESDEN LINE PROTECTIVE RELAYING | GPC | 2026 | 12/1/2026
213 | 20874 | GTC: BARNESVILLE PRIMARY- BARNESVILLE #1 115KV RECONDUCTOR | GTC | 2026 | 12/1/2026
208 | 20273 | GTC: DRESDEN 500KV BUS EXPANSION | GTC | 2026 | 12/1/2026
214 | 20002 | GTC: GORDON - SANDERSVILLE #1 115KV LINE REBUILD | GTC | 2026 | 12/1/2026
211 | 20151 | CC - CASS PINE 230/25 NEW SUB - QCELLS - CC IMPROVEMENTS | GPC | 2026 | 12/31/2026
206 | 19287 | GRADY-WEST END 115KV REBUILD | GPC | 2026 | 12/31/2026
208 | 19363 | MORROW - MOUNTAIN VIEW 115 KV REBUILD | GPC | 2026 | 12/31/2026
213 | 18832 | MEAG: FORTSON 230KV SUBSTATION MODERNIZATION | MEAG | 2027 | 1/13/2027
201 | 20509 | CC - EMBLEM RIVERSIDE CUSTOMER SUB (FLEXENTIAL) | GPC | 2027 | 3/1/2027
211 | 19635 | GTC: HICKORY LEVEL - VILLA RICA 230KV LINE RECONDUCTOR | GTC | 2027 | 5/1/2027
208 | 19601 | MORROW - YATES COMMON 115KV LINE UPGRADE | GPC | 2027 | 5/1/2027
211 | 15879 | POSSUM BRANCH - YATES COMMON 115KV REBUILD (YATES TO CLEM) | GPC | 2027 | 5/1/2027
208 | 20771 | CC - GULLATT ROAD TRANSMISSION IMPROVEMENTS | GPC | 2027 | 6/1/2027
208 | 18736 | CC - MICROSOFT - SHUGART (CCO06) | GPC | 2027 | 6/1/2027
201 | 20781 | CC - SUMMER LAKE - VILLA RICA 230KV REBUILD (CC IMPROVMNT) | GPC | 2027 | 6/1/2027
208 | 20736 | CC - TA REALTY ELLENWOOD NETWORK IMPROVEMENTS | GPC | 2027 | 6/1/2027
212 | 20234 | DOYLE - LG&E MONROE 230KV - JACKS CREEK LOOP IN | GPC | 2027 | 6/1/2027
201 | 20858 | GTC: ADAMSVILLE - BUZZARD ROOST 230KV REBUILD | GTC | 2027 | 6/1/2027
201 | 20776 | GTC: DOUGLASVILLE - VILLA RICA 230KV REBUILD (CC IMPROVEMENT) | GTC | 2027 | 6/1/2027
212 | 20778 | GTC: DOYLE - WINDER PRIMARY 230KV LINE JUMPER REPLACEMENT | GTC | 2027 | 6/1/2027
216 | 19358 | GTC: EAST MOULTRIE - HIGHWAY 112 230 KV LINE | GTC | 2027 | 6/1/2027
212 | 09662 | GTC: EAST WALTON 500/230KV PROJECT | GTC | 2027 | 6/1/2027
201 | 20505 | GTC: GARRETT RD - V. RICA 230KV LINE RECONDUCTOR (CC NET IM) | GTC | 2027 | 6/1/2027
214 | 19622 | GTC: RIDDLEVILLE BUS REPLACEMENT | GTC | 2027 | 6/1/2027
206 | 19606 | GTC: SKC 115KV BUS AND JUMPER REPLACEMENT | GTC | 2027 | 6/1/2027
214 | 20020 | GTC: SOUTH HAZLEHURST - NEW LACY 230KV LINE | GTC | 2027 | 6/1/2027
201 | 20506 | GTC: SWITCH WAY - THORNTON ROAD 230KV LINE REBUILD | GTC | 2027 | 6/1/2027
218 | 18668 | JESUP - OFFERMAN 115KV REBUILD | GPC | 2027 | 6/1/2027
202 | 10143 | LAWRENCEVILLE - WINDER 115KV LINE REBUILD | GPC | 2027 | 6/1/2027
202 | 10481 | LAWRENCEVILLE - WINDER PRIMARY 230KV LINE REBUILD | GPC | 2027 | 6/1/2027
215 | 20264 | MEAG: RAY PLACE RD - WARRENTON PRIMARY | MEAG | 2027 | 6/1/2027
214 | 19248 | SANDERSVILLE #1 - WADLEY PRI. 115KV REBUILD/RECONDUCTOR | GPC | 2027 | 6/1/2027
219 | 20785 | SAV: GOSHEN (SAV) - KRAFT 115KV LINE REBUILD | SAV | 2027 | 6/1/2027
219 | 20065 | SAV: GOSHEN (SAV) - MCINTOSH 115KV LINE REBUILD | SAV | 2027 | 6/1/2027
208 | 20717 | CC - TOMOCHICHI 500/230KV SOLUTION (CC NETWORK IMPROVEMENTS) | GPC | 2027 | 7/15/2027
214 | 18573 | GRID - ARKWRIGHT - LLOYD SHOALS 115KV | GPC | 2027 | 7/30/2027
214 | 20591 | GTC: EATONTON PRIMARY (035591) - LICK CREEK 115KV REBUILD | GTC | 2027 | 12/1/2027
212 | 17977 | ATHENA - EAST WATKINSVILLE 115 KV (REBUILD) | GPC | 2027 | 12/31/2027
211 | 20150 | CC - HILL VIEW & GRASSY HOLLOW SUB - CC IMPROVEMENTS | GPC | 2027 | 12/31/2027
211 | 20024 | DYER ROAD - EAST ROANOKE 115KV (REBUILD) | GPC | 2027 | 12/31/2027
214 | 19997 | AULTMAN ROAD-PERRY 115KV LINE REBUILD | GPC | 2028 | 6/1/2028
201 | 20797 | CC - EAST VILLA RICA AREA SWITCHING STATION (CC IMPROVEMENT) | GPC | 2028 | 6/1/2028
211 | 20774 | CC - VILLA RICA UPGRADES (CC NETWORK IMPROVEMENTS) | GPC | 2028 | 6/1/2028
214 | 21048 | FITZGERALD - PITTS 115 KV LINE REBUILD | GPC | 2028 | 6/1/2028
213 | 08458 | GTC: BARNESVILLE - SOUTH GRIFFIN 230KV PROJECT | GTC | 2028 | 6/1/2028
216 | 20503 | GTC: BARNEYVILLE - EAST MOULTRIE 115KV NEW LINE | GTC | 2028 | 6/1/2028
214 | 20873 | GTC: BONAIRE PRIMARY 500/230KV XFMR REPLCMNT & RELAY MOD | GTC | 2028 | 6/1/2028
212 | 19992 | GTC: BOSTWICK - EAST SOCIAL CIRCLE 230KV RECONDUCTOR | GTC | 2028 | 6/1/2028
206 | 20777 | JACK MCDONOUGH - NORTHWEST (BLACK) 230KV RECONDUCTOR | GPC | 2028 | 6/1/2028
216 | 19629 | MEAG: BRUMBLEY CREEK - SOUTH BAINBRIDGE 115KV REBUILD | MEAG | 2028 | 6/1/2028
216 | 19630 | MEAG: THOMASVILLE 230/115KV AUTOBANK REPLACEMENT | MEAG | 2028 | 6/1/2028
213 | 20482 | PITTMAN ROAD - WEST POINT DAM (USA) 115KV REBUILD | GPC | 2028 | 6/1/2028
208 | 20656 | PLANT YATES BREAKER AND HALF STATION | GPC | 2028 | 6/1/2028
219 | 20783 | SAV: COLEMAN - DEAN FOREST 115KV LINE REBUILD | SAV | 2028 | 6/1/2028
219 | 20407 | SAV: MAGNOLIA - TRUMAN PARKWAY 115KV REBUILD | SAV | 2028 | 6/1/2028
201 | 21069 | SMART VALVES AT EAST VILLA RICA SWITCHING STATION | GPC | 2028 | 6/1/2028
214 | 20768 | SOUTH MACON 115KV BUSES 1 & 2 REPLACEMENT | GPC | 2028 | 6/1/2028
208 | 20274 | UNION CITY - YATES 230KV (BLACK) LINE REBUILD | GPC | 2028 | 6/1/2028
213 | 13166 | FIRST AVENUE - NORTH COLUMBUS 115KV LINE REBUILD | GPC | 2028 | 12/1/2028
214 | 20586 | GTC: NORTH DUBLIN 230/115KV TRANSFORMERS AND BUS-TIE BREAKER | GTC | 2028 | 12/1/2028
208 | 21062 | ASHLEY PARK-WANSLEY 500KV | GPC | 2029 | 6/1/2029
216 | 10222 | BLAKELY PRIMARY - HUCKLEBERRY 115KV REBUILD | GPC | 2029 | 6/1/2029
214 | 21047 | BROADWAY - ECHECONNEE 115 KV LINE REBUILD | GPC | 2029 | 6/1/2029
213 | 16887 | BUTLER - THOMASTON 230KV LINE CONVERSION | GPC | 2029 | 6/1/2029
201 | 21036 | BUZZARD ROOST - FACTORY SHOALS 230KV NEW LINE | GPC | 2029 | 6/1/2029
206 | 21142 | CONYERS - KLONDIKE 230 KV SECOND LINE | GPC | 2029 | 6/1/2029
206 | 21138 | GLENWOOD SPRINGS - PORTERDALE PRIMARY 230KV LINE SWITCH REPL | GPC | 2029 | 6/1/2029
213 | 21112 | GTC: BARNESVILLE PRIMARY - THOMASTON 230KV | GTC | 2029 | 6/1/2029
202 | 10814 | GTC: BAY CREEK 230/115KV SECOND AUTO TRANSFORMER | GTC | 2029 | 6/1/2029
214 | 21140 | GTC: BONAIRE PRIMARY - EASTMAN PRIMARY 115 KV LINE REBUILD | GTC | 2029 | 6/1/2029
201 | 20849 | GTC: CLIFTONDALE - LINE CREEK 230KV LINE | GTC | 2029 | 6/1/2029
213 | 19950 | GTC: DRESDEN - TALBOT 500KV LINE | GTC | 2029 | 6/1/2029
202 | 20760 | GTC: HOPEWELL 230/115 KV BANK A | GTC | 2029 | 6/1/2029
201 | 21123 | GTC: TENASKA - WANSLEY 500KV NEW LINE | GTC | 2029 | 6/1/2029
206 | 21141 | LLOYD SHOALS - PORTERDALE PRIMARY 115KV REBUILD | GPC | 2029 | 6/1/2029
216 | 20285 | LOWER RIVER - WEBB (APC) 115KV RECONDUCTOR | GPC | 2029 | 6/1/2029
212 | 19621 | MCEVER ROAD - SHOAL CREEK 115KV REBUILD | GPC | 2029 | 6/1/2029
218 | 20346 | MCMANUS - WEST BRUNSWICK 115KV REBUILD | GPC | 2029 | 6/1/2029
214 | 17706 | MEAG: AULTMAN ROAD - FORT VALLEY #1 115 KV REBUILD | MEAG | 2029 | 6/1/2029
216 | 11051 | MEAG: SLAPPEY DRIVE - WESTOVER 115KV LINE REBUILD | MEAG | 2029 | 6/1/2029
202 | 20757 | NORCROSS - NORTH DRUID HILLS 115KV REBUILD | GPC | 2029 | 6/1/2029
219 | 21006 | SAV: BOULEVARD - MAGNOLIA 115 KV LINE REBUILD | SAV | 2029 | 6/1/2029
219 | 21023 | SAV: DEAN FOREST - LITTLE OGEECHEE 230 KV REBUILD | SAV | 2029 | 6/1/2029
219 | 20989 | SAV: RICE HOPE NEW AUTO TRANSFORMER | SAV | 2029 | 6/1/2029
216 | 13628 | SOUTH BAINBRIDGE - SINAI (FPL) 115KV LINE RECONDUCTOR | GPC | 2029 | 6/1/2029
202 | 20248 | BAY CREEK - CONYERS 230KV REBUILD | GPC | 2029 | 12/31/2029
211 | 21129 | ANNISTON - HAMMOND 230KV LINE | GPC | 2030 | 6/1/2030
201 | 20764 | ATKINSON - NORTHSIDE DRIVE 115KV REBUILD | GPC | 2030 | 6/1/2030
201 | 20761 | ATKINSON - NORTHWEST 115KV REBUILD | GPC | 2030 | 6/1/2030
212 | 21130 | CC - NORTH GEORGIA DATA NETWORK UPGRADES | GPC | 2030 | 6/1/2030
212 | 10478 | CORNELIA - TALLULAH LODGE 115KV REBUILD | GPC | 2030 | 6/1/2030
212 | 18669 | DU: DAWSON CROSSING - NELSON (WHITE) 115 KV REBUILD | DU | 2030 | 6/1/2030
201 | 21097 | EAST POINT - TRIBUTARY 230KV REBUILD | GPC | 2030 | 6/1/2030
208 | 20480 | EAST POINT - UNION CITY 230KV BLACK LINE RECONDUCTOR | GPC | 2030 | 6/1/2030
214 | 19627 | ECHECONNEE-WELLSTON 115KV LINE REBUILD | GPC | 2030 | 6/1/2030
216 | 21063 | FARLEY (APC)-TAZEWELL 500KV | GPC | 2030 | 6/1/2030
212 | 12120 | GAINESVILLE #2 - MCEVER ROAD 115 KV REBUILD | GPC | 2030 | 6/1/2030
214 | 20298 | GLENWOOD SPRINGS - LAKE OCONEE 115KV LINE REBUILD | GPC | 2030 | 6/1/2030
213 | 21128 | GOAT ROCK REACTORS INSTALLATION | GPC | 2030 | 6/1/2030
215 | 19996 | GOLDENS CREEK - WARRENTON PRIMARY 230KV REBUILD | GPC | 2030 | 6/1/2030
214 | 20428 | GORDON-SANDERSVILLE #1 115KV LINE REBUILD (DEEPSTEP-SAND #6) | GPC | 2030 | 6/1/2030
215 | 21116 | GOSHEN AREA STRATEGIC SOLUTION | GPC | 2030 | 6/1/2030
208 | 21073 | GTC: BIG SMARR - TOMOCHICHI 500KV | GTC | 2030 | 6/1/2030
201 | 21014 | GTC: BUZZARD ROOST - CAVENDER DRIVE 230KV NEW LINE | GTC | 2030 | 6/1/2030
201 | 21013 | GTC: CAVENDER DRIVE 500/230KV AUTOBANK | GTC | 2030 | 6/1/2030
212 | 20375 | GTC: EAST WATKINSVILLE 230 KV STATION MODIFICATION | GTC | 2030 | 6/1/2030
212 | 21111 | GTC: HARTWELL DAM - HARTWELL ENERGY 230KV SERIES REACTORS | GTC | 2030 | 6/1/2030
212 | 21113 | GTC: HARTWELL ENERGY - MIDDLE FORK 230KV LINE | GTC | 2030 | 6/1/2030
212 | 21131 | GTC: POND FORK - MIDWAY 115KV LINE | GTC | 2030 | 6/1/2030
214 | 21077 | GTC: ROCKVILLE - TIGER CREEK -WARTHEN 500KV LINES | GTC | 2030 | 6/1/2030
216 | 21076 | GTC: TALLBOT #2 - TAZEWELL 500KV LINE | GTC | 2030 | 6/1/2030
214 | 21094 | GTC: TIGER CREEK- ROCKVILLE-NORTH SPA 230KV PROJECT | GTC | 2030 | 6/1/2030
212 | 20789 | JEFFERSON ROAD - WINDER PRIMARY 115KV REBUILD | GPC | 2030 | 6/1/2030
216 | 20284 | KETTLE CREEK PRIMARY - PINE GROVE PRIMARY 115KV REBUILD | GPC | 2030 | 6/1/2030
215 | 21118 | MEAG: ATHENA - WARRENTON 230KV CONVERSION | MEAG | 2030 | 6/1/2030
201 | 20857 | NEW CAVENDER DRIVE - TRIBUTARY 230KV LINE | GPC | 2030 | 6/1/2030
214 | 21093 | NORTH SPA 230KV STRATEGIC PROJECT | GPC | 2030 | 6/1/2030
212 | 19995 | TALLULAH LODGE - TOCCOA 115 KV REBUILD | GPC | 2030 | 6/1/2030
201 | 21098 | TRIBUTARY - THORNTON RD 230KV REBUILD | GPC | 2030 | 6/1/2030
213 | 20160 | THOMASTON 230 NEW BUILD SUB | GPC | 2030 | 11/1/2030
216 | 18848 | BAINBRIDGE TRANSMISSION: EAST RIVER ROAD, EAST BAINBRIDGE | GPC | 2030 | 12/31/2030
214 | 19626 | GLENWOOD SPRINGS 115KV CAP BANK | GPC | 2030 | 12/31/2030
208 | 20690 | EAST POINT - UNION CITY (WHITE) 230KV REBUILD | GPC | 2031 | 5/1/2031
202 | 19632 | AVERY - HOPEWELL 115KV RECONDUCTOR | GPC | 2031 | 6/1/2031
211 | 10811 | BOWEN #10 500/230KV AUTOBANK REPLACEMENT | GPC | 2031 | 6/1/2031
215 | 20756 | HATCH - WADLEY 500 KV LINE STRATEGIC PROJECT | GPC | 2031 | 6/1/2031
214 | 21099 | MEAG: PIO NONO 230/115KV AREA SOLUTION | MEAG | 2031 | 6/1/2031
213 | 21114 | MEAG: SOUTH GRIFFIN 230/115KV BANK #5 | MEAG | 2032 | 6/1/2032
219 | 20784 | SAV: COLEMAN - MELDRIM 115KV LINE REBUILD | SAV | 2032 | 6/1/2032
214 | 20767 | ARKWRIGHT BUS AND JUMPER REPLACEMENT | GPC | 2033 | 6/1/2033
202 | 20758 | BAY CREEK - CONYERS 230KV LIMITING ELEMENT REPLACEMENT | GPC | 2033 | 6/1/2033
215 | 20793 | EVANS PRIMARY - THURMOND DAM (USA) #5 115KV REBUILD | GPC | 2033 | 6/1/2033
215 | 20794 | EVANS PRIMARY - THURMOND DAM (USA) #6 115KV REBUILD | GPC | 2033 | 6/1/2033
212 | 12217 | GTC: CENTER PRIMARY - CLARKSBORO 230 KV REBUILD | GTC | 2033 | 6/1/2033
212 | 20773 | GTC: CLARKSBORO - WINDER PRIMARY 230KV REBUILD | GTC | 2033 | 6/1/2033
212 | 12147 | GTC: EAST SOCIAL CIRCLE - SNELLVILLE 230KV EQUIPMENT UPGRADE | GTC | 2033 | 6/1/2033
212 | 21075 | GTC: EAST WALTON - MIDDLE FORK 500KV | GTC | 2033 | 6/1/2033
212 | 20791 | GTC: SHOAL CREEK - SOUTH HALL 230KV REBUILD | GTC | 2033 | 6/1/2033
212 | 21053 | MCEVER ROAD - SHOAL CREEK 115KV REBUILD PHASE III | GPC | 2033 | 6/1/2033
212 | 09661 | MCGRAU FORD - MIDDLE FORK 500KV LINE PROJECT | GPC | 2033 | 6/1/2033
219 | 20796 | SAV: MELDRIM BANK D REPLACEMENT | SAV | 2033 | 6/1/2033
215 | 14222 | THOMSON PRIMARY 230/115KV SECOND TRANSFORMER | GPC | 2033 | 6/1/2033
202 | 20759 | WINDER PRIMARY 230KV BUS 1-2 PARALLEL BUS-TIE INSTALLATION | GPC | 2033 | 6/1/2033
216 | 10487 | PINE GROVE PRIMARY - WEST VALDOSTA 115 KV RECONDUCTOR | GPC | 2033 | 12/31/2033
212 | 18700 | DAWSON CROSSING - GAINESVILLE #1 115 KV | GPC | 2034 | 6/1/2034
219 | 20787 | SAV: LITTLE OGEECHEE 230/115KV BANK REPLACEMENT | SAV | 2034 | 6/1/2034
215 | 17993 | EVANS PRIMARY - THOMSON PRIMARY 115KV REBUILD | GPC | 2034 | 12/31/2034

## Notes
Source | File | Notes
DESC | 2024-2028-2million-and-above-project-descriptions.pdf | 44 planned/in-progress transmission projects ($2M+), 2024-2028 5-year budget. Extracted directly, no CEII markings present.
Georgia Power (GA ITS 10-Year Plan) | 2025_IRP_Volume_3_PUBLIC_DISCLOSURE.pdf | 195 rows from '2024 GA ITS Ten-Year Plan (2025-2034)', Section D.1.a Executive Summary & Project List (PDF pages 7-20 of that embedded document). Cost columns in the source are redacted (marked REDACTED) -- this is the intended public-disclosure version; only non-cost fields (zone, project name, sponsor, need date) are retained here.
IMPORTANT |  | This 10-Year Plan list bundles ALL Georgia ITS participants, not just Georgia Power (GPC): sponsor values include GPC, GTC (Georgia Transmission Corp), MEAG, DU (Dalton Utilities), and SAV (Savannah-area zone). If the challenge wants Georgia Power specifically, filter the 'Sponsor' column to GPC before building the overlap table -- left all sponsors in this raw extraction so that filtering decision stays visible and reversible.
EXCLUDED |  | The Cancelled Projects List and Completed Projects List sections (pages 21-22 of the embedded plan) were deliberately excluded -- those are no longer planned/active projects.