## Overlap Table
DESC ID | DESC Name | DESC In-Service Date | GPC ID | GPC Name | GPC In-Service Date | Distance (km) | Distance (mi) | Geographic Tier | Day Gap | Timeline Overlap (<= 365 days)
6852 | Urquhart – Toolebeck 115kV line: Rebuild | 2026-08-12 | 16007 | FENWICK STREET - SAND BAR FERRY 115KV (RECONDUCTOR/REBUILD) | 2026-06-01 | 4.308 | 2.68 | Under 8 km -- can share site logistics (laydown yards, deliveries) | 72 | Yes
6810 O | Urquhart – Aiken PSA 46 kV: Rebuild | 2027-12-31 | 16007 | FENWICK STREET - SAND BAR FERRY 115KV (RECONDUCTOR/REBUILD) | 2026-06-01 | 4.308 | 2.68 | Under 8 km -- can share site logistics (laydown yards, deliveries) | 578 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 20989 | SAV: RICE HOPE NEW AUTO TRANSFORMER | 2029-06-01 | 5.565 | 3.46 | Under 8 km -- can share site logistics (laydown yards, deliveries) | 1248 | No
6809 G | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV | 2025-12-31 | 20793 | EVANS PRIMARY - THURMOND DAM (USA) #5 115KV REBUILD | 2033-06-01 | 11.074 | 6.88 | Under 40 km -- can share crews & equipment | 2709 | No
6809 G | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV | 2025-12-31 | 20794 | EVANS PRIMARY - THURMOND DAM (USA) #6 115KV REBUILD | 2033-06-01 | 11.074 | 6.88 | Under 40 km -- can share crews & equipment | 2709 | No
6809 E | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV Rebuilds | 2024-12-31 | 20793 | EVANS PRIMARY - THURMOND DAM (USA) #5 115KV REBUILD | 2033-06-01 | 11.074 | 6.88 | Under 40 km -- can share crews & equipment | 3074 | No
6809 E | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV Rebuilds | 2024-12-31 | 20794 | EVANS PRIMARY - THURMOND DAM (USA) #6 115KV REBUILD | 2033-06-01 | 11.074 | 6.88 | Under 40 km -- can share crews & equipment | 3074 | No
6809 G | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV | 2025-12-31 | 16007 | FENWICK STREET - SAND BAR FERRY 115KV (RECONDUCTOR/REBUILD) | 2026-06-01 | 15.183 | 9.43 | Under 40 km -- can share crews & equipment | 152 | Yes
6809 E | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV Rebuilds | 2024-12-31 | 16007 | FENWICK STREET - SAND BAR FERRY 115KV (RECONDUCTOR/REBUILD) | 2026-06-01 | 15.183 | 9.43 | Under 40 km -- can share crews & equipment | 517 | No
6809 G | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV | 2025-12-31 | 17993 | EVANS PRIMARY - THOMSON PRIMARY 115KV REBUILD | 2034-12-31 | 23.362 | 14.52 | Under 40 km -- can share crews & equipment | 3287 | No
6809 E | Stevens Creek - Hooks 115kV/LR Plumb Branch 46kV Rebuilds | 2024-12-31 | 17993 | EVANS PRIMARY - THOMSON PRIMARY 115KV REBUILD | 2034-12-31 | 23.362 | 14.52 | Under 40 km -- can share crews & equipment | 3652 | No
06810 H | Summerville 115kV Loop: Rebuild | 2024-12-31 | 20873 | GTC: BONAIRE PRIMARY 500/230KV XFMR REPLCMNT & RELAY MOD | 2028-06-01 | 24.417 | 15.17 | Under 40 km -- can share crews & equipment | 1248 | No
6810 O | Urquhart – Aiken PSA 46 kV: Rebuild | 2027-12-31 | 20793 | EVANS PRIMARY - THURMOND DAM (USA) #5 115KV REBUILD | 2033-06-01 | 27.014 | 16.79 | Under 40 km -- can share crews & equipment | 1979 | No
6810 O | Urquhart – Aiken PSA 46 kV: Rebuild | 2027-12-31 | 20794 | EVANS PRIMARY - THURMOND DAM (USA) #6 115KV REBUILD | 2033-06-01 | 27.014 | 16.79 | Under 40 km -- can share crews & equipment | 1979 | No
6852 | Urquhart – Toolebeck 115kV line: Rebuild | 2026-08-12 | 20793 | EVANS PRIMARY - THURMOND DAM (USA) #5 115KV REBUILD | 2033-06-01 | 27.014 | 16.79 | Under 40 km -- can share crews & equipment | 2485 | No
6852 | Urquhart – Toolebeck 115kV line: Rebuild | 2026-08-12 | 20794 | EVANS PRIMARY - THURMOND DAM (USA) #6 115KV REBUILD | 2033-06-01 | 27.014 | 16.79 | Under 40 km -- can share crews & equipment | 2485 | No
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 21073 | GTC: BIG SMARR - TOMOCHICHI 500KV | 2030-06-01 | 28.469 | 17.69 | Under 40 km -- can share crews & equipment | 1826 | No
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 20067 | SAV: DEPTFORD - MAGNOLIA 115KV RECONDUCTOR | 2025-06-01 | 29.141 | 18.11 | Under 40 km -- can share crews & equipment | 0 | Yes
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 20066 | SAV: BOULEVARD - DEPTFORD 115KV RECONDUCTOR | 2026-06-01 | 30.419 | 18.9 | Under 40 km -- can share crews & equipment | 365 | Yes
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 20783 | SAV: COLEMAN - DEAN FOREST 115KV LINE REBUILD | 2028-06-01 | 31.068 | 19.3 | Under 40 km -- can share crews & equipment | 883 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 21023 | SAV: DEAN FOREST - LITTLE OGEECHEE 230 KV REBUILD | 2029-06-01 | 31.068 | 19.3 | Under 40 km -- can share crews & equipment | 1248 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 21073 | GTC: BIG SMARR - TOMOCHICHI 500KV | 2030-06-01 | 31.212 | 19.39 | Under 40 km -- can share crews & equipment | 1613 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 20796 | SAV: MELDRIM BANK D REPLACEMENT | 2033-06-01 | 32.154 | 19.98 | Under 40 km -- can share crews & equipment | 2709 | No
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 20989 | SAV: RICE HOPE NEW AUTO TRANSFORMER | 2029-06-01 | 33.349 | 20.72 | Under 40 km -- can share crews & equipment | 1461 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 20066 | SAV: BOULEVARD - DEPTFORD 115KV RECONDUCTOR | 2026-06-01 | 33.839 | 21.03 | Under 40 km -- can share crews & equipment | 152 | Yes
06810 H | Summerville 115kV Loop: Rebuild | 2024-12-31 | 18679 | DU: EAST DALTON - OOSTANAULA 115KV REBUILD | 2026-06-01 | 34.813 | 21.63 | Under 40 km -- can share crews & equipment | 517 | No
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 21006 | SAV: BOULEVARD - MAGNOLIA 115 KV LINE REBUILD | 2029-06-01 | 34.814 | 21.63 | Under 40 km -- can share crews & equipment | 1461 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 20067 | SAV: DEPTFORD - MAGNOLIA 115KV RECONDUCTOR | 2025-06-01 | 35.177 | 21.86 | Under 40 km -- can share crews & equipment | 213 | Yes
0139 M,N | Okatie 230-115kV Substation, Jasper – Yemassee 230kV #1 Fold-in | 2024-12-31 | 20989 | SAV: RICE HOPE NEW AUTO TRANSFORMER | 2029-06-01 | 35.198 | 21.87 | Under 40 km -- can share crews & equipment | 1613 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 21006 | SAV: BOULEVARD - MAGNOLIA 115 KV LINE REBUILD | 2029-06-01 | 35.2 | 21.87 | Under 40 km -- can share crews & equipment | 1248 | No
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 20783 | SAV: COLEMAN - DEAN FOREST 115KV LINE REBUILD | 2028-06-01 | 35.769 | 22.23 | Under 40 km -- can share crews & equipment | 1096 | No
6808 S | Okatie-Bluffton 115kV: Rebuild | 2025-06-01 | 21023 | SAV: DEAN FOREST - LITTLE OGEECHEE 230 KV REBUILD | 2029-06-01 | 35.769 | 22.23 | Under 40 km -- can share crews & equipment | 1461 | No
6810 O | Urquhart – Aiken PSA 46 kV: Rebuild | 2027-12-31 | 17993 | EVANS PRIMARY - THOMSON PRIMARY 115KV REBUILD | 2034-12-31 | 36.229 | 22.51 | Under 40 km -- can share crews & equipment | 2557 | No
6852 | Urquhart – Toolebeck 115kV line: Rebuild | 2026-08-12 | 17993 | EVANS PRIMARY - THOMSON PRIMARY 115KV REBUILD | 2034-12-31 | 36.229 | 22.51 | Under 40 km -- can share crews & equipment | 3063 | No
06367 D - G | Jasper – Okatie 230 kV #2: Construct | 2025-12-31 | 20175 | CC - PROJECT CHRONOS- SK/HYUNDAI | 2025-12-31 | 38.142 | 23.7 | Under 40 km -- can share crews & equipment | 0 | Yes